## Team Task Allocation
No. | Team Member | Assigned Responsibility | Expected Work / Evidence | Status
1 | MOHD AQIB | Dataset collection and download | Confirm source URL, download archive, record citation/licence. | Pending
2 | VIKAS VERMA | Dataset inspection and quality | Check file parsing, missing values, duplicates, source counts, and label quality. | Pending
3 | YUG SAXENA | Text preprocessing and cleaning | Review whitespace normalization, empty text removal, and duplicate handling. | Pending
4 | PRIYAMVADA UPADHYAY | Sentiment labels and definitions | Document 1=Positive and 0=Negative; explain absence of Neutral class. | Pending
5 | PRASHANT KUMAR | Exploratory data analysis | Prepare sentiment/source/length summaries and explain patterns. | Pending
6 | AKASH YADAV | TF-IDF feature extraction | Explain unigram/bigram TF-IDF and why it is fitted on training data only. | Pending
7 | SAYEDA MAHAK MUSAWWIR | Logistic Regression model | Explain model training, parameters, and validation predictions. | Pending
8 | PIYUSH GUPTA | Multinomial Naive Bayes model | Explain model training and probability-based classification. | Pending
9 | VIRENDRA PAL | Team Leader and project integration | Coordinate work, verify notebook execution, review report/slides, and approve final submission. | Pending
10 | VIJAY GANGWAR | Model evaluation and F1 | Check accuracy, macro precision/recall/F1, and class-wise report. | Pending
11 | ATUL KUMAR | Confusion matrices and comparison | Interpret false positives/false negatives and compare both algorithms. | Pending
12 | SAJAL YADAV | Error analysis | Manually inspect at least five errors and document wording-based reasons. | Pending
13 | POOJA SAHU | Graphs and visualizations | Check sentiment balance, source/length graphs, confusion matrices, and metric plot. | Pending
14 | RISHABH PUSHKAR | Documentation and presentation | Prepare report, limitations/future scope, references, and final PPT. | Pending